## Budget Sheet
Category | Budgeted Amount | Actual Amount | Variance | Comments
Labor | 100000 | 95000 | 5000 | On track
Materials | 50000 | 55000 | -5000 | Over budget
Equipment | 20000 | 18000 | 2000 | On track
Travel | 10000 | 8000 | 2000 | On track
Miscellaneous | 5000 | 7000 | -2000 | Over budget
Total | 185000 | 183000 | 2000

## Risk Management
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Mitigation Plan | Owner
1 | Delay in material delivery | 4 | 3 | Identify alternative suppliers | Project Manager
2 | Budget overrun | 3 | 4 | Implement cost control measures | Finance Manager
3 | Equipment failure | 2 | 5 | Regular maintenance and contingency plan | Operations Manager
4 | Team member unavailability | 3 | 3 | Cross-training team members | HR Manager
5 | Regulatory changes | 2 | 4 | Stay updated with regulations and compliance | Compliance Officer